## Slide 1: Lecture – 8 Project Planning and Scheduling
SWE 205 - Introduction to Software Engineering
Software Project Plan
  Milestones & Deliverables
Project Scheduling
  Bar charts
Ch 23

## Slide 2: Project Planning
Probably the most time-consuming project management activity.
  Iterative process which is only complete when the project itself is complete.
Project plan is regularly revised;
  As more project information is available.
Introduction
Project Plan
Project Scheduling
Summary
Page 2 of 23

## Slide 3: Project planning process
Assess the project constraints
  Required delivery date
  Staff available
  Overall budget ……..
Define Process milestone and deliverables
Introduction
Project Plan
Project Scheduling
Summary
Page 3 of 23

## Slide 4: Milestones & Deliverables
Milestones
  end-point of a process activity.
  points in the schedule against which you can assess progress,
  e.g., handover of the system for testing.
Deliverables
  project results delivered to customers.
  e.g. a requirements document for the system
Introduction
Project Plan
Project Scheduling
Summary
Page 4 of 23

## Slide 5: Planning stages
Proposal stage: when you are bidding for a contract to develop or provide a software system.
Project startup phase: when you have to plan who will work on the project, how the project will be broken down into increments, how resources will be allocated across your company, etc.
Periodically throughout the project: when you modify your plan in the light of experience gained and information from monitoring the progress of the work.
Introduction
Project Plan
Project Scheduling
Summary
Page 5 of 23

## Slide 6: Plan-driven development
Plan-driven or plan-based development is an approach to software engineering where the development process is planned in detail.
  Plan-driven development is based on engineering project management techniques and is the ‘traditional’ way of managing large software development projects.
A project plan is created that records the work to be done, who will do it, the development schedule and the work products.
Managers use the plan to support project decision making and as a way of measuring progress.
23.2
Introduction
Project Plan
Project Scheduling
Summary
Page 6 of 23

## Slide 7: Plan-driven development – pros and cons
early planning allows organizational issues (availability of staff, other projects, etc.) to be closely taken into account, and that potential problems and dependencies are discovered before the project starts, rather than once the project is underway.
many early decisions have to be revised because of changes to the environment in which the software is to be developed and used.
Introduction
Project Plan
Project Scheduling
Summary
Page 7 of 23

## Slide 8: Project plans
Project Plan
  Introduction
  Project organization
  Risk analysis
  Hardware and software resource requirements
  Work breakdown
  Project schedule
  Monitoring and reporting mechanisms
project plan sets out the resources available to the project, the work breakdown and a schedule for carrying out the work.
23.2.1
Introduction
Project Plan
Project Scheduling
Summary
Page 8 of 23

## Slide 9: Project plan supplements
Plan | Description
Quality plan | Describes the quality procedures and standards that will be used in a project.
Validation plan | Describes the approach, resources, and schedule used for system validation.
Configuration management plan | Describes the configuration management procedures and structures to be used.
Maintenance plan | Predicts the maintenance requirements, costs, and effort.
Staff development plan | Describes how the skills and experience of the project team members will be developed.
Introduction
Project Plan
Project Scheduling
Summary
Page 9 of 23

## Slide 10: The planning process
Project planning is an iterative process that starts when you create an initial project plan during the project startup phase.
Plan changes are inevitable.
  As more information about the system and the project team becomes available during the project, you should regularly revise the plan to reflect requirements, schedule and risk changes.
  Changing business goals also leads to changes in project plans. As business goals change, this could affect all projects, which may then have to be re-planned.
23.2.2
Introduction
Project Plan
Project Scheduling
Summary
Page 10 of 23

## Slide 11: The project planning process
Introduction
Project Plan
Project Scheduling
Summary
Page 11 of 23

## Slide 12: Project Scheduling
Split project into tasks and estimate time and resources required to complete each task.
Organize tasks concurrently to make optimal use of workforce.
Minimize task dependencies to avoid delays caused by one task waiting for another to complete.
23.3
Introduction
Project Plan
Project Scheduling
Summary
Page 12 of 23

## Slide 13: Project scheduling
Definition: is the process of deciding how the work in a project will be organized as separate tasks, and when and how these tasks will be executed.
estimate the calendar time needed to complete each task, the effort required and who will work on the tasks that have been identified.
estimate the resources needed to complete each task, such as the disk space required on a server, the time required on specialized hardware, such as a simulator, and what the travel budget will be.
Introduction
Project Plan
Project Scheduling
Summary
Page 13 of 23

## Slide 14: Project scheduling activities: How?
Split project into tasks and estimate time and resources required to complete each task.
Organize tasks concurrently to make optimal use of workforce.
Minimize task dependencies to avoid delays caused by one task waiting for another to complete.
Dependent on project managers intuition and experience.
Introduction
Project Plan
Project Scheduling
Summary
Page 14 of 23

## Slide 15: The project scheduling process
Allocate People to Activities
Identify Activities
Identify Activity Dependencies
Estimate Resources
Create Project Charts
Bar charts describing the project schedule
Software Requirements and Design Information
Introduction
Project Plan
Project Scheduling
Summary
Page 15 of 23

## Slide 16: Scheduling problems
Estimating the difficulty of problems and hence the cost of developing a solution is hard.
Productivity is not proportional to the number of people working on a task.
Adding people to a late project makes it later because of communication overheads.
The unexpected always happens. Always allow contingency in planning.
Introduction
Project Plan
Project Scheduling
Summary
Page 16 of 23

## Slide 17: Schedule representation
Graphical notations are normally used to illustrate the project schedule.
These show the project breakdown into tasks. Tasks should not be too small. They should take about a week or two.
Bar charts are the most commonly used representation for project schedules. They show the schedule as activities or resources against time.
Introduction
Project Plan
Project Scheduling
Summary
Page 17 of 23

## Slide 18: Tasks, durations, and dependencies
Task | Effort (person-days) | Duration (days) | Dependencies
T1 | 15 | 10 | 
T2 | 8 | 15 | 
T3 | 20 | 15 | T1 (M1)
T4 | 5 | 10 | 
T5 | 5 | 10 | T2, T4 (M3)
T6 | 10 | 5 | T1, T2 (M4)
T7 | 25 | 20 | T1 (M1)
T8 | 75 | 25 | T4 (M2)
T9 | 10 | 15 | T3, T6 (M5)
T10 | 20 | 15 | T7, T8 (M6)
T11 | 10 | 10 | T9 (M7)
T12 | 20 | 10 | T10, T11 (M8)
Introduction
Project Plan
Project Scheduling
Summary
Page 18 of 23

## Slide 19: Activity bar chart
Introduction
Project Plan
Project Scheduling
Summary
Page 19 of 23
start
T1
T2
(M1/T1)
T3
T4
T5
(M3/T2&T4)
T6
(M4/T1&T2)
T7
(M2/T4)
T8
(M5/T3&T6)
T9
T10
T11
finish

## Slide 20: Activity
Think about a software that can assist you to draw such charts?
Introduction
Project Plan
Project Scheduling
Summary
Page 20 of 23

## Slide 21: Activity Network
Minimum time required to finish
the project. (critical path)
Introduction
Project Plan
Project Scheduling
Summary
Page 21 of 23

## Slide 22: Staff allocation chart
Introduction
Project Plan
Project Scheduling
Summary
Page 22 of 23

## Slide 23: Key Points
Plan-driven development
  organized around a complete project plan that defines the project activities, the planned effort, the activity schedule and who is responsible for each activity.
Project scheduling
  Bar charts and staffing timelines are the most commonly used schedule representations
Milestone is a predictable outcome of an activity where some formal report of progress should be presented to management.
A deliverable is a milestone that is delivered to the project customer.
Introduction
Project Plan
Project Scheduling
Summary
Page 23 of 23