## Slide 1: Chapter 9: Project Resource Management
Note: The slides are adopted from: Kathy Schwalbe. Information Technology Project Management, Course Technology, 9th Edition, 2018 [with modifications]

## Slide 2: Learning Objectives (1 of 2)
Explain the importance of good resource management on projects, including the current state of the global IT workforce and future implications for IT
Define project resource management and understand its processes
Summarize key concepts for managing people by understanding theories of motivation, influence, and power; how people and teams can become more effective; emotional intelligence; and leadership
Discuss resource management planning and be able to create a human resource plan, project organizational chart, responsibility assignment matrix, and resource histogram
Describe the process of estimating activity resources

## Slide 3: Learning Objectives (2 of 2)
Discuss issues that are typically involved in resource acquisition, particularly as they involve resource assignments, resource loading, and resource leveling
Assist in team development with training, team-building activities, and reward systems
Explain and apply several tools and techniques to help manage a project team and summarize general advice on managing teams
Summarize the process of controlling resources
Describe how project management software can assist in project resource management
Discuss considerations for agile/adaptive environments

## Slide 4: The Importance of Resource Management
People determine the success and failure of organizations and projects
  Most project managers agree that managing human resources effectively is one of the toughest challenges they face
  Managing people is a vital component of project resource management

## Slide 5: The Global IT Workforce
Although there have been ups and downs in the IT labor market, there will always be a need for good IT workers
  By June of 2017, there were almost 4.3 billion mobile-broadband subscriptions
  By 2020, ICT spending is projected to grow to nearly $5.5 trillion
  Jobs available to IT professionals are expected to increase by 12 percent by 2024
  Project management is number three on Computerworld’s hottest tech list

## Slide 6: Implications for the Future of IT Human Resource Management
Proactive organizations are addressing human resource needs
  Improving benefits
  Redefining work hours and incentives
  Finding future workers

## Slide 7: Global Issues
In 2013, Yahoo’s CEO issued a memo stating that employees could no longer work from home, causing quite a stir throughout the world
Diebold’s CEO took the opposite approach and started recruiting employees who wanted to work from home, luring the best and brightest workers from Yahoo and other companies cutting back on telecommuting

## Slide 8: What Went Wrong?
CompTIA found a gap between skills that employers wanted and what they actually found in the IT workforce
  68 percent of IT firms report having a very challenging time finding new staff
  52 percent of organizations report having job openings, and 33 percent say they are understaffed, while 42 percent say they are fully staffed but want to hire more people in order to expand
  58 percent of businesses are concerned about the quality and quantity of IT talent available for hire
  Top technology priorities in this survey included security, data storage, and network infrastructure
  The number one strategy to handle understaffing is requiring workers to put in more hours
  94 percent of IT professionals plan to pursue more training

## Slide 9: What is Project Resource Management? (1 of 2)
Making the most effective use of the human and physical resources involved with a project
  Planning resource management
  Estimating activity resources
  Acquiring resources
  Developing the project team
  Managing the project team
  Controlling resources

## Slide 10: What is Project Resource Management? (2 of 2)

## Slide 11: Keys to Managing and Leading People
Psychologists and management theorists have devoted much research and thought to the field leading people at work
  Motivation theories
  Influence and power
  Effectiveness
  Emotional intelligence
  Leadership

## Slide 12: Motivation Theories
Intrinsic motivation causes people to participate in an activity for their own enjoyment
  Example: some people love to read, write, or play an instrument because it makes them feel good
Extrinsic motivation causes people to do something for a reward or to avoid a penalty
  Example: some young children would prefer not to play an instrument, but they do because they receive a reward or avoid a punishment for doing so

## Slide 13: Maslow’s Hierarchy of Needs (1 of 2)
Abraham Maslow argued that humans possess unique qualities that enable them to make independent choices, thus giving them control of their destiny
  Developed a hierarchy of needs; states that people’s behaviors are guided or motivated by a sequence of needs

## Slide 14: Maslow’s Hierarchy of Needs (2 of 2)

## Slide 15: Herzberg’s Motivational-Hygiene Theory (1 of 2)
Frederick Herzberg distinguished between motivational factors and hygiene factors
  Motivational factors: factors that cause job satisfaction
  Hygiene factors: could cause job dissatisfaction

## Slide 16: Herzberg’s Motivational-Hygiene Theory (2 of 2)
Hygiene Factors | Motivators
Larger salaries | Achievement
More supervision | Recognition
More attractive work environment | Work itself
Computer or other required equipment | Responsibility
Health benefits | Advancement
Training | Growth
Table 9-1 Examples of Herzberg’s hygiene factors and
motivators

## Slide 17: McClelland’s Acquired-Needs Theory
Specific needs are acquired or learned over time and shaped by life experiences
  Achievement (nAch): achievers like challenging projects with achievable goals and regular feedback
  Affiliation (nAff): people with high nAff desire harmonious relationships and need to feel accepted by others, so managers should try to create a cooperative work environment for them
  Power: (nPow): people with a need for power desire either personal power (not good) or institutional power (good for the organization)

## Slide 18: McGregor’s Theory X and Y
Douglas McGregor popularized the human relations approach to management in the 1960s
  Theory X: assumes workers dislike and avoid work, so managers must use coercion, threats and various control schemes to get workers to meet objectives
  Theory Y: assumes individuals consider work as natural as play or rest and enjoy the satisfaction of esteem and self-actualization needs
  Theory Z: introduced in 1981 by William Ouchi and is based on the Japanese approach to motivating workers, emphasizing trust, quality, collective decision making, and cultural values

## Slide 19: Influence and Power (1 of 3)
Thamhain and Wilemon: ways to have influence on projects
  Authority: legitimate hierarchical right to issue orders
  Assignment: ability to influence a worker's later work assignments
  Budget: ability to authorize others' use of discretionary funds
  Promotion: ability to improve a worker's position
  Money: ability to increase a worker's pay and benefits
  Penalty: ability to cause punishment
  Work challenge: ability to assign work that capitalizes on a worker's enjoyment of doing a particular task
  Expertise: perceived special knowledge that others deem important
  Friendship: ability to establish friendly personal relationships between the project manager and others

## Slide 20: Influence and Power (2 of 3)
Ways to influence
  Project managers who use work challenges and expertise to influence people projects are more likely to succeed
  Projects are more likely to fail when project managers rely too heavily on authority, money, or penalty

## Slide 21: Influence and Power (3 of 3)
Power is the potential ability to influence behavior to get people to do things they would not otherwise do
  Power is much stronger than influence, because it is often used to force people to change their behavior
Types of power
  Coercive
  Legitimate
  Expert
  Reward
  Referent

## Slide 22: Covey and Improving Effectiveness
Project managers can apply Covey’s seven habits to improve effectiveness on projects
  Be proactive
  Begin with the end in mind
  Put first things first
  Think win/win
  Seek first to understand, then to be understood
  Synergize
  Sharpen the saw

## Slide 23: Leadership
There is no one best way to be a leader
  Most experts agree that the best leaders are able to adapt their style to needs of the situation
  It is important to understand and pay attention to concepts of motivation, influence, power, effectiveness, emotional intelligence, and leadership in all project processes

## Slide 24: What Went Right?
PMI introduced the PMI Talent Triangle® in 2015 to emphasize the need for more than technical skills for project managers
  The Talent Triangle® includes:
    Technical project management
    Strategic and business management
    Leadership

## Slide 25: Developing the Resource Management Plan and Team Charter (1 of 6)
Involves identifying and documenting project resources, roles, responsibilities, skills, and reporting relationships
  Can be separated into a human resource management plan and a physical resource management plan
Contents include:
  Project organizational charts
  Responsibility assignment matrixes
  Staffing management plan and resource histograms
  Team charters

## Slide 26: Developing the Resource Management Plan and Team Charter (2 of 6)

## Slide 27: Developing the Resource Management Plan and Team Charter (3 of 6)

## Slide 28: Developing the Resource Management Plan and Team Charter (4 of 6)

## Slide 29: Developing the Resource Management Plan and Team Charter (5 of 6)
 | Car Owner | Shop Owner | Mechanic | Parts Supplier
Pay for parts and services | A, R | C |  | 
Determine parts and services needed | C |  | A, R | C
Supply parts |  | C | C | A, R
Install parts | I | A | R | 
Table 9-2 Sample RACI chart

## Slide 30: Developing the Resource Management Plan and Team Charter (6 of 6)

## Slide 31: Estimating Activity Resources
Tools that can assist in resource estimating
  Expert judgment
  Various estimating approaches
  Data analysis
  Project management software
  Meetings

## Slide 32: Acquiring Resources
During the late 1990s, the IT job market became extremely competitive
  Today, many organizations again face a shortage of IT staff
Regardless of the current job market, acquiring qualified IT professionals is critical

## Slide 33: Resource Assignment
After developing resource requirements, project managers must work with other people in their organizations to assign them to their projects or to acquire additional human or physical resources needed for the project
  Organizations that do a good job of staff acquisition have good staffing plans
  It is very important to consider the needs of individuals and the organization when making recruiting and retention decisions

## Slide 34: Best Practice
Best practices can be applied to include the best places for people to work
  Fortune Magazine lists the “100 Best Companies to Work For” in the United States every year, with Google taking the honors for the eighth time in 2017
  Working Mothers Magazine lists the best companies in the U.S. for women based on benefits for working families
  The Times online provides the Sunday Times list of the “100 Best Companies to Work For,” a key benchmark against which U.K. companies can judge their performance as employers

## Slide 35
http://fortune.com/best-companies/
2016
2017
2018
2019

## Slide 36: Resource Loading (1 of 2)
Resource loading refers to the amount of individual resources an existing schedule requires during specific time periods
  Helps project managers develop a general understanding of the demands a project will make on the organization’s resources and individual people’s schedules
Overallocation means more resources than available are assigned to perform work at a given time

## Slide 37: Resource Loading (2 of 2)

## Slide 38: Resource Leveling (1 of 2)
Resource leveling is a technique for resolving resource conflicts by delaying tasks
  Main purpose is to create a smoother distribution of resource usage
Benefits of resource leveling
  When resources are used on a more constant basis, they require less management
  May enable project managers to use a just-in-time inventory type of policy for using subcontractors or other expensive resources
  Results in fewer problems for project personnel and accounting department
  Often improves morale

## Slide 39: Resource Leveling (2 of 2)

## Slide 40: Developing the Project Team (1 of 2)
The main goal of team development is to help people work together more effectively to improve project performance
  It takes teamwork to successfully complete most projects
Tuckman model describes five stages of team development
  Forming: introduction to team members
  Storming: team members have different opinions
  Norming: team members have developed a common working method
  Performing: emphasis on reaching the team goals rather than a team process
  Adjourning: break-up after completion

## Slide 41: Developing the Project Team (2 of 2)
Training
  Project managers often recommend that people take specific training courses to improve individual and team development
Team-building activities
  Physical challenges
  Psychological preference indicator tools
Teamwork1.mp4
Teamwork2.wmv
Teamwork3.mp4

## Slide 42: The Social Styles Profile
People are perceived as behaving primarily in one of four zones, based on their assertiveness and responsiveness
  Drivers
  Expressives
  Analyticals
  Amiables

## Slide 43: Reward and Recognition Systems
Team-based reward and recognition systems can promote teamwork
  Focus on rewarding teams for achieving specific goals
    If management rewards teamwork, they will promote or reinforce the philosophy that people work more effectively in teams
Project managers must continually assess their team’s performance
  When they find areas in which individuals or the entire team can improve, it’s their job to find the best way to develop their people and improve performance

## Slide 44: Managing the Project Team
Project managers must lead their teams in performing various project activities
After assessing team performance and related information, the project manager must make several decisions
  Changes to be requested
  Corrective or preventive actions
  Updates needed

## Slide 45: Tools and Techniques for Managing Project Teams (1 of 4)
Several tools and techniques are available to assist in managing project teams
  Interpersonal and team skills
  Project management information systems
  Conflict management

## Slide 46: Tools and Techniques for Managing Project Teams (2 of 4)
Conflict handling modes
  Confrontation: directly face a conflict using a problem-solving approach
  Compromise: use a give-and-take approach
  Smoothing: de-emphasize areas of difference and emphasize areas of agreement
  Forcing: win-lose approach
  Withdrawal: retreat or withdraw from an actual or potential disagreement
  Collaborating: decision makers incorporate different viewpoints and insights to develop consensus and commitment

## Slide 47: Tools and Techniques for Managing Project Teams (3 of 4)

## Slide 48: Tools and Techniques for Managing Project Teams (4 of 4)
Conflict can be good
  Conflict often produces important results, such as new ideas, better alternatives, and motivation to work harder and more collaboratively
  Groupthink: conformance to the values or ethical standards of a group; can develop if there are no conflicting viewpoints
  Research suggests that task-related conflict often improves team performance, but emotional conflict often depresses team performance

## Slide 49: General Advice on Managing Teams (1 of 2)
Five dysfunctions of teams
  Absence of trust
  Fear of conflict
  Lack of commitment
  Avoidance of accountability
  Inattention to results

## Slide 50: General Advice on Managing Teams (2 of 2)
General advice
  Be patient and kind with your team
  Fix the problem instead of blaming people
  Establish regular, effective meetings
  Allow time for teams to go through the basic team-building stages
  Limit the size of work teams to three to seven members
  Plan some social activities to help project team members and other stakeholders get to know each other better
  Stress team identity
  Nurture team members and encourage them to help each other
  Acknowledge individual and group accomplishments
  Take additional actions to work with virtual team members

## Slide 51: Controlling Resources
Ensuring physical resources assigned to the project are available as planned
  Also involves monitoring the planned versus actual resources utilization and taking corrective actions as needed

## Slide 52: Using Software to Assist in Resource Management
Software can help in producing a simple responsibility assignment matrix or resource histograms
Software includes several features related to human resource management
  Assigning and tracking resources
  Leveling resources
  Resource usage reports
  Overallocated resource reports
  To-do lists

## Slide 53: Considerations for Agile/Adaptive Environments
Teams are important on all types of projects, as is collaboration, problem solving, and knowledge sharing
  On agile projects, team members are usually fully dedicated to a single team
    Relationships are based on trust, and collaboration is continuously improved using regular feedback

## Slide 54: Chapter Summary
Project resource management includes the processes required to make the most effective use of the people involved with a project
  Planning resources
  Estimating activity resources
  Acquiring resources
  Developing the team
  Managing the team
  Controlling resources