## Slide 1: Chapter 6: Project Schedule Management
Note: The slides are adopted from: Kathy Schwalbe. Information Technology Project Management, Course Technology, 9th Edition, 2018 [with modifications]

## Slide 2: Learning Objectives (1 of 2)
Illustrate the importance that project schedules and good project schedule management can have in helping to make projects successful
Discuss the process of planning schedule management
Define activities as the basis for developing project schedules
Describe how project managers use network diagrams and dependencies to assist in activity sequencing
Explain how various tools and techniques help project managers perform activity duration estimates
Use a Gantt chart for planning and tracking schedule information, find the critical path for a project, and describe how critical chain scheduling and the Program Evaluation and Review Technique (PERT) affect schedule development

## Slide 3: Learning Objectives (2 of 2)
Compare how schedule management is addressed using Agile vs. more predictive project approaches
Discuss how reality checks and discipline are involved in controlling and managing changes to the project schedule
Describe how project management software can assist in project schedule management and review words of caution before using this software
Discuss considerations for agile/adaptive environments

## Slide 4: The Importance of Project Schedules (1 of 3)
Managers often cite delivering projects on time as one of their biggest challenges
  Time has the least amount of flexibility; it passes no matter what happens on a project
Individual work styles and cultural differences may also cause schedule conflicts
  Different cultures and even entire countries have different attitudes about schedules

## Slide 5: The Importance of Project Schedules (2 of 3)
Project time management processes
  Planning schedule management
  Defining activities
  Sequencing activities
  Estimating activity durations
  Developing the schedule
  Controlling the schedule

## Slide 6: The Importance of Project Schedules (3 of 3)

## Slide 7: Planning Schedule Management
Elements of a schedule management plan
  Project schedule model development
  Scheduling methodology
  Level of accuracy and units of measure
  Control thresholds
  Rules of performance measurement
  Reporting formats
  Process descriptions

## Slide 8: Defining Activities (1 of 2)
Defining activities involves identifying the specific actions that will produce the project deliverables in enough detail to determine resource and schedule estimates
  Activity list: a tabulation of activities to be included on a project schedule
    Activity name, activity identifier or number, and brief description of the activity
  Activity attributes provide more information
    Predecessors, successors, logical relationships, leads and lags, resource requirements, constraints, imposed dates, and assumptions related to the activity

## Slide 9: Defining Activities (2 of 2)
A milestone is a significant event that normally has no duration
  It often takes several activities and a lot of work to complete a milestone
  They’re useful tools for setting schedule goals and monitoring progress
    Examples: obtaining customer sign-off on key documents or completion of specific products

## Slide 10: Sequencing Activities (1 of 6)
Sequencing process involves evaluating the reasons for dependencies and the different types of dependencies
  A dependency or relationship is the sequencing of project activities or tasks
    Mandatory dependencies: inherent in the nature of the work being performed on a project, sometimes referred to as hard logic
    Discretionary dependencies: defined by the project team, sometimes referred to as soft logic. and should be used with care since they may limit later scheduling options
    External dependencies: involve relationships between project and non-project activities

## Slide 11: Sequencing Activities (2 of 6)
Network diagrams are the preferred technique for showing activity sequencing
  Schematic display of the logical relationships among, or sequencing of, project activities
  Two main formats are the arrow and precedence diagramming methods

## Slide 12: Sequencing Activities (3 of 6)

## Slide 13: Sequencing Activities (4 of 6)
Arrow diagramming method (ADM) (i.e., activity-on-arrow network diagrams)
  Activities are represented by arrows
  Nodes or circles are the starting and ending points of activities
  Only show finish-to-start dependencies
  Refer to the text for the step-by-step process of creating AOA diagrams
Precedence diagramming method (PDM)
  Network diagramming technique in which boxes represent activities
Types of dependencies or relationships between activities
  Finish-to-start
  Start-to-start
  Finish-to-finish
  Start-to-finish

## Slide 14: Sequencing Activities (5 of 6)

## Slide 15: Sequencing Activities (6 of 6)

## Slide 16: Estimating Activity Durations
Duration includes the actual amount of time worked on an activity plus elapsed time
  Effort is the number of workdays or work hours required to complete a task and does not normally equal duration
People doing the work should help create estimates
  An expert should review them
A three-point estimate is an estimate that includes an optimistic, most likely, and pessimistic estimate
  Three-point estimates are needed for PERT and Monte Carlo simulations

## Slide 17: Developing the Schedule
Uses results of the other time management processes to determine the start and end date of the project
  Ultimate goal is to create a realistic project schedule that provides a basis for monitoring project progress for the time dimension of the project
Important tools and techniques
  Gantt charts
  Critical path analysis
  Critical chain scheduling
  PERT analysis

## Slide 18: Gantt Charts (1 of 5)
Provide a standard format for displaying project schedule information by listing project activities and corresponding start and finish dates in a calendar form
  Symbols
    Black diamond: milestones
    Thick black bars: summary tasks
    Light gray horizontal bars: durations of tasks
    Arrows: dependencies between tasks

## Slide 19: Gantt Charts (2 of 5)

## Slide 20: Gantt Charts (3 of 5)

## Slide 21: Gantt Charts (4 of 5)
Adding milestones to Gantt charts
  Many people like to focus on meeting milestones, especially for large projects
    Milestones emphasize important events or accomplishments on projects
SMART Criteria for milestones
  Specific
  Measurable
  Assignable
  Realistic
  Time-framed

## Slide 22: Gantt Charts (5 of 5)

## Slide 23: Critical Path Method (CPM) (1 of 2)
Network diagramming technique used to predict total project duration
  Critical path: series of activities that determine the earliest time by which the project can be completed
    The longest path through the network diagram and has the least amount of slack or float; amount of time an activity may be delayed without delaying a succeeding activity or the project finish date
Calculating the critical path
  Develop a good network diagram and add the duration estimates for all activities on each path through the network diagram
    Longest path is the critical path
  If one or more of the activities on the critical path takes longer than planned, the whole project schedule will slip unless the project manager takes corrective action

## Slide 24: Simple Example of Determining the Critical Path
Consider the following project network diagram. Assume all times are in days.
How many paths are on this network diagram?
How long is each path?
Which is the critical path?
What is the shortest amount of time needed to complete this project?
2
3
4
5
A=2
B=5
C=2
D=7
1
6
F=2
E=1
start
finish

## Slide 25: Critical Path Method (CPM) (2 of 2)

## Slide 26: Growing Grass Can Be on the Critical Path
The fact that its name includes the word critical does not mean that it includes all critical activities
  Only accounts for time
There can be more than one critical path if the lengths of two or more paths are the same
  Project managers should closely monitor performance of activities on the critical path to avoid late project completion
  Critical path can change as the project progresses

## Slide 27: Using Critical Path Analysis to Make Schedule Trade-Offs (1 of 3)
Free slack or free float
  Amount of time an activity can be delayed without delaying the early start of any immediately following activities
Total slack or total float
  Amount of time an activity may be delayed from its early start without delaying the planned project finish date
Forward pass
  Determines the early start and finish dates
Backward pass
  Determines the late start and finish dates

## Slide 28: Using Critical Path Analysis to Make Schedule Trade-Offs (2 of 3)

## Slide 29: Using Critical Path Analysis to Make Schedule Trade-Offs (3 of 3)
Task Name | Start | Finish | Late Start | Late Finish | Free Slack | Total Slack
A | 8/3/15 | 8/3/15 | 8/5/15 | 8/5/15 | 0d | 2d
B | 8/3/15 | 8/4/15 | 8/3/15 | 8/4/15 | 0d | 0d
C | 8/3/15 | 8/5/15 | 8/5/15 | 8/7/15 | 0d | 2d
D | 8/4/15 | 8/7/15 | 8/6/15 | 8/11/15 | 2d | 2d
E | 8/5/15 | 8/11/15 | 8/5/15 | 8/11/15 | 0d | 0d
F | 8/5/15 | 8/10/15 | 8/14/15 | 8/17/15 | 7d | 7d
G | 8/6/15 | 8/13/15 | 8/10/15 | 8/17/15 | 0d | 2d
H | 8/12/15 | 8/19/15 | 8/12/15 | 8/19/15 | 0d | 0d
I | 8/14/15 | 8/17/15 | 8/18/15 | 8/19/15 | 2d | 2d
J | 8/20/15 | 8/24/15 | 8/20/15 | 8/24/15 | 0d | 0d
Table 6-1 Free and Total Float or Slack for Project X

## Slide 30: Using the Critical Path to Shorten a Project Schedule
Main techniques for shortening schedules
  Shortening durations of critical activities/tasks by adding more resources or changing their scope
  Crashing activities by obtaining the greatest amount of schedule compression for the least incremental cost
  Fast tracking activities by doing them in parallel or overlapping them

## Slide 31: Crashing and fast tracking
Overlapped
Tasks or fast
tracking
Shortened
duration thru
crashing
Original
schedule

## Slide 32: Importance of Updating Critical Path Data
It is important to update the schedule with actual data
  Note actual activity durations as they are completed
  Revise estimates for activities in progress
  Monitor changes to make informed decisions

## Slide 33: Critical Chain Scheduling (1 of 4)
Considers limited resources when creating a project schedule and includes buffers to protect the project completion date
  Uses the Theory of Constraints (TOC): management philosophy developed by Eliyahu M. Goldratt; attempts to minimize multitasking when a resource works on more than one task at a time

## Slide 34: Critical Chain Scheduling (2 of 4)

## Slide 35: Critical Chain Scheduling (3 of 4)
Additional concepts
  Buffer: additional time to complete a task
  Murphy’s Law: if something can go wrong, it will
  Parkinson’s Law: work expands to fill the time allowed
  Project buffer: additional time added before the project’s due date
  Feeding buffers: additional time added before tasks on the critical path

## Slide 36: Critical Chain Scheduling (4 of 4)

## Slide 37: What Went Right?
Scheduling at healthcare clinic’s can be more efficient by using critical chain scheduling
  National University Hospital in Singapore decreased patient admission times by more than 50 percent
    Improved scheduling lowered average wait times, which went from six to eight hours to less than three hours
    63 percent of patients were admitted in less than 1.5 hours

## Slide 38: Program Evaluation and Review Technique (PERT)
Network analysis technique used to estimate project duration when there is a high degree of uncertainty about the individual activity duration estimates
  Uses probabilistic time estimates: duration estimates based on using optimistic, most likely, and pessimistic estimates of activity durations
  By using the PERT weighted average for each activity duration estimate, total project duration estimate takes into account the risk or uncertainty in the individual activity estimates

## Slide 39: Agile and Schedule Management
Core values of the Manifesto for Agile Software Development
  Customer collaboration over contract negotiation
  Responding to change over following a plan
Example: product owner defines and prioritizes the work to be done within a sprint
  Collaboration and time management are designed into the process

## Slide 40: Controlling the Schedule
Goals of schedule control
  Know the status of the schedule
  Influence the factors that cause schedule changes
  Determine that the schedule has changed
  Manage changes when they occur
Main inputs to schedule control
  Project management plan
  Project documents
  Work performance data
  Organizational process assets

## Slide 41: Reality Checks on Scheduling and the Need for Discipline
Important activities
  Review the draft schedule or estimated completion date in the project charter
  Prepare a more detailed schedule with the project team
  Make sure the schedule is realistic and followed
  Alert top management well in advance if there are schedule problems

## Slide 42: Using Software to Assist in Project Schedule Management
Software for facilitating communications helps people exchange schedule-related information
  Decision support models help analyze trade-offs that can be made to address schedule issues
  Project management software can help in various time management areas

## Slide 43: Words of Caution on Using Project Management Software
Many people misuse project management software because they don’t understand important concepts and have not had training
  Example: dependencies must be entered to have dates adjust automatically and to determine the critical path
Many project management software programs come with templates or sample files
  It is very easy to use these files without considering unique project needs
  Project managers and their teams should be careful not to rely too much on templates or sample files and ignore the unique concerns of their particular projects

## Slide 44: Considerations for Agile/Adaptive Environments
Schedule management is radically different using Agile and Scrum
  Projects that rely heavily on the critical path method consider meeting the project’s estimated completion date as a crucial component of success
  Agile projects may not even need to estimate activity durations or project schedules at all; overall project completion time is not important

## Slide 45: Chapter Summary
Project time management is often cited as the main source of conflict on projects
  Most IT projects exceed time estimates
Main processes
  Plan schedule management
  Define activities
  Sequence activities
  Estimate activity durations
  Develop schedule
  Control schedule